## AI Arch
Capability | Technology
Ticket Classification | ML Model
Routing | Rules + ML
Ticket Prioritization | ML + Rules
Knowledge Search | Vector DB + LLM
Ticket Summarization | LLM
Agent Copilot | LLM
Auto Reply Drafting | LLM
Workflow Execution | Rules Engine
Auto resolution | LLM + RAG + ML
Vector DB | Pinecone
LLM | OpenAI (GPT-mini, others)
DB | PostGre SQL
Back-end | C# | Kumar
Frontend | Angular.js | Kumar

## RACI
Role | Responsibility | Name
Product Owner (You) | Requirements & Prioritization | Yash
Solution Architect | Solution Governance | Yash/MIT
AI Architect | AI Design | Yash/MIT
Program/Project Manager | Delivery Tracking | Yash
QA Lead | Testing | Yash/MIT/Business Team
Testing | Unit testing | MIT
| 1st Level QA/Integration testing | Yash
| 2nd Level QA | Balakumaran/Kadiravan/Jira/ACM Leads
| UAT | Adrenalin Support/Product/Custom solutions Team
Development | Code & DB Design | MIT
Security Reviewer | Security & Compliance | Kumar | RBAC & Application security
Technical Project Manager | Technical guidance | Kumar

## Metrics
Metric | Target
Classification Accuracy | >85%
Priority Accuracy | >80%
Routing Accuracy | >85%
KB Retrieval Precision | >90%
Co-pilot - quality of response & speed | Individually verifiable

## Dev-Test-Deploy
| Function | Exit Criteria |  | Expected end date | Responsibility
Sprint 0 | Foundation | Exit Criteria |  | 2026-06-12 | MIT
| Authentication | User login working
| User Management | Role security validated
| Organization Setup | Able to add groups, depatments
Sprint 1 | Ticketing Engine | Exit Criteria |  | 2026-06-12 | MIT
| Ticket lifecycle | End-to-end ticket lifecycle works
Ticket creation
Ticket updates
Internal notes
Attachments
Watchers
Ticket merging
Ticket splitting
Sprint 2 | Workflow engine | Exit Criteria |  | 2026-06-12 | MIT
| Assignment | Rules engine
| Escalation | Manual assignment & workflow
Reassignment
Approval workflows
Sprint 3 | Knowledge Base | Exit criteria |  | 2026-06-19 | MIT
| Create Articles | KB searchable
| Implement Search | KB Retrieval Precision | >90%
Article Management
Sprint 4 | AI Layer - 1 | Exit Criteria |  | 2026-06-26 | MIT
| Classification | 85% classification accuracy
Train Model
Ticket Category
Product Area
Sprint 5 | Copilot | Co-pilot effective & efficient |  | 2026-07-03 | MIT
Ticket Summaries
Suggested Responses
Knowledge Recommendations
Sprint 6 | AI Layer - 2 | Exit Criteria |  | 2026-07-17 | MIT
| Routing | Classification Accuracy | >85%
| Prioritization | Priority Accuracy | >80%
| Auto resolution | Routing Accuracy | >85%
| Root Cause identification | Auto-resolve repetitive tickets
| Training & Fine Tuning | Incident clustering
Problem identification
Sprint 7 | SLA Engine | Exit criteria |  | 2026-07-31 | MIT
| SLA Monitoring | SLA tracking operational
| SLA Policies | SLA countdown
| Escalations | Warning thresholds
| Notifications | Breach detection
Sprint 8 | Jira/ACM flow | Exit criteria |  | 2026-08-07 | MIT
| Jira flow | End-to-end ticket lifecycle works
ACM flow
Sprint 9 | SIT | Exit criteria |  | 2026-08-21 | MIT/Yash
| Ticket Flows | All validatations pass
| Creation | Auto-resolve repetitive tickets
| Escalation | Root cause identification & clustering
| Closure | Generate KB articles from resolved tickets
SLA
Breaches
Notifications
AI
Classification
Copilot
Sprint 10 | UAT & Pilot | Exit criteria |  | 2026-09-04 | Business/MIT
| UAT Wave 1 | Critical defects - 0
| End Customers | High defects <5
| Validate: | UAT Pass Rate >95%
Portal
Ticket creation
| Status updates | Measure
Ticket handling time
| UAT Wave 2 | AI acceptance rate
| Support Agents | Suggested response usage
| Validate: | Resolution quality
Daily ticket handling
Knowledge search
Copilot
UAT Wave 3
Support Managers
Validate:
Workflows
Reports
Escalations
Sprint 11 | Migration Sprint 1 |  |  | 2026-09-18 | Business/MIT
| Extract from Freshdesk, Jira |  |  |  | Business
Contacts
Companies
Tickets
Attachments
| Migrate data |  |  |  | MIT
| Validation |  |  |  | Business
Sprint 12 | Parallel Run |  |  | 2026-10-02 | Business
Run Freshdesk & ITSM tool in parallel for 1-2 weeks
Check for AI part
Inform customer about new Tool
Sprint 13 | Cutover Run
| Final migration dry run |  |  | 2026-10-10 | Business
Rollback planning
Production readiness review
| Export Final Delta |  |  |  | Business/MIT
New tickets
Updated tickets
Comments
Attachments
| Validate |  |  |  | Business
Ticket counts
Users
Attachments
SLAs
| Cutover signoff |  |  |  | Business
Sprint 14 | Production Rollout |  |  | 2026-10-11 | Business
Switch:
| Email routing |  |  |  | Business
| Portal URLs |  |  |  | Business
| Notification services |  |  |  | MIT
Sprint 15 | Hypercare Week 1-2 |  |  | 2026-10-19 | Business
Track:
Incidents
Errors
AI accuracy
User satisfaction
Transition to BAU support

## Governance
Weekly Governance
Weekly Sprint Review
Weekly Architecture Review
AI Model Review every 2 weeks
Monthly Steering Committee

## AI-Specific Deliverables
S NO | Name | Responsibility
1 | AI Architecture Document | MIT
2 | Prompt Library | MIT
3 | RAG Design Document | MIT
4 | ML Training Strategy | MIT
5 | AI Evaluation Framework | MIT
6 | Hallucination Testing Report | MIT
7 | AI Security Assessment | MIT
8 | AI Monitoring Dashboard | MIT